## Gantt Chart
Feed the Future Zone of Influence Survey Core Gantt Chart
Feed the Future Zone of Influence Survey Tasks and Timeline |  | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Activity planning | bar: MONTH 1
2 | Inception visit | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the study design and accompanying implementation plan | bar: MONTH 1 to MONTH 3
5 | Develop and issue RFP (if required) | bar: MONTH 2
6 | Prepare the sampling design | bar: MONTH 2
7 | Coordinate with national statistical office to select PSUs | bar: MONTH 2 to MONTH 3
8 | Prepare the analysis plan | bar: MONTH 2 to MONTH 3
9 | Undertake country-specific customization of the core questionnaire (paper version) | bar: MONTH 2 to MONTH 3
10 | Questionnaire translation (paper version) | bar: MONTH 3
11 | Submit application for review to the IRB | bar: MONTH 3 to MONTH 4
12 | Establish range values for purposes of implementing range checks | bar: MONTH 3 to MONTH 4
13 | Prepare unit conversion tables | bar: MONTH 3 to MONTH 4
14 | Subcontract to local partner organization | bar: MONTH 4
15 | Implement questionnaire pretest | bar: MONTH 4 to MONTH 5
16 | Material provisioning (tablets, scales, and height boards) | bar: MONTH 4 to MONTH 5
17 | Develop pretest and pilot protocols | bar: MONTH 4 to MONTH 5
18 | Questionnaire programming (either for tablets or for data entry program) | bar: MONTH 4 to MONTH 6
19 | Preparation of manuals: | bar: MONTH 4 to MONTH 6
19a - Interviewer Manual | bar: MONTH 4 to MONTH 6
19b - Supervisor and Field Editor Manual | bar: MONTH 4 to MONTH 6
19c - Fieldwork Organization Manual | bar: MONTH 4 to MONTH 6
19d - GPS Manual | bar: MONTH 4 to MONTH 6
19e - Quality Control and Support Team Manual (rotating supervisory team) | bar: MONTH 4 to MONTH 6
19f - Listing Manual | bar: MONTH 4 to MONTH 6
20 | Develop field check tables | bar: MONTH 4 to MONTH 7
21 | Prepare data structure and codebook | bar: MONTH 4 to MONTH 7
22 | Develop and code programming specifications (tablets only) | bar: MONTH 4 to MONTH 7
23 | Prepare data cleaning plan | bar: MONTH 4 to MONTH 7
24 | Develop data monitoring plan | bar: MONTH 4 to MONTH 7
Feed the Future Zone of Influence Survey Tasks and Timeline |  | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
25 | Develop fieldwork management and monitoring plan | bar: MONTH 4 to MONTH 7
26 | Develop interviewer training plans and supporting materials | bar: MONTH 4 to MONTH 7
26a - Training plan | bar: MONTH 4 to MONTH 7
26b - Agenda (facilitator and trainee versions) | bar: MONTH 4 to MONTH 7
26c - Attendance sheets | bar: MONTH 4 to MONTH 7
26d - Quizzes | bar: MONTH 4 to MONTH 7
26e - Role play exercises | bar: MONTH 4 to MONTH 7
26f - Demonstration of field check tables and interpretation | bar: MONTH 4 to MONTH 7
26g - Demonstration of real-time remote fieldwork monitoring (if planned) | bar: MONTH 4 to MONTH 7
26h - Tablet training materials (if relevant) | bar: MONTH 4 to MONTH 7
26i - Agriculture-specific training materials | bar: MONTH 4 to MONTH 7
26j - Anthropometry training materials (if relevant) | bar: MONTH 4 to MONTH 7
26k - Biomarker training materials (if relevant) | bar: MONTH 4 to MONTH 7
26l - Supervisor and field editor training materials (incl. assignment and control sheets) | bar: MONTH 4 to MONTH 7
26m - Data entry staff and supervisor training plan and materials | bar: MONTH 4 to MONTH 7
26n - IT staff training plan and materials (if relevant) | bar: MONTH 4 to MONTH 7
27 | Implement listing operation | bar: MONTH 6 to MONTH 7
28 | Implement cleaning of listing data and selection of households (on a rolling basis) | bar: MONTH 6 to MONTH 7
29 | Ensure that IRB approval has been received | bar: MONTH 7
30 | Implement training of trainers | bar: MONTH 7 to MONTH 8
31 | Implement pretest (as part of training of trainers) | bar: MONTH 7 to MONTH 8
32 | Implement main training | bar: MONTH 8
33 | Implement pilot (as part of main training) | bar: MONTH 8
34 | Implement data entry/data management pilot as part of all-systems fieldwork pilot | bar: MONTH 8
35 | Prepare data weighting protocol | bar: MONTH 8
36 | Implement fieldwork | bar: MONTH 9 to MONTH 13
37 | Generate field check tables | bar: MONTH 9 to MONTH 14
38 | Weight the data | bar: MONTH 14
39 | Prepare protocol for rendering data suitable for public use | bar: MONTH 14
40 | Clean the data | bar: MONTH 14 to MONTH 15
41 | Prepare data quality assessment memo | bar: MONTH 16
42 | Analyze the data | bar: MONTH 16 to MONTH 19
43 | Prepare final report tables | bar: MONTH 18 to MONTH 19
44 | Draft final report text | bar: MONTH 17 to MONTH 19
45 | Prepare internal use data files (maintains some PII, e.g., GPS coordinates) | bar: MONTH 17 to MONTH 20
46 | Prepare public use data files (excludes PII) | bar: MONTH 18 to MONTH 20
47 | Enter values in Feed the Future Monitoring System | bar: MONTH 20
Notes: RFP – request for proposal; PSU – primary sampling unit; IRB – institutional review board; PII – personally identifiable information
This Gantt chart is predicated on the use of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized for country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented here.