## About the Survey Tracker
FEED THE FUTURE SURVEY IMPLEMENTATION DOCUMENT
Survey Implementation Tracker Zone of Influence Survey [COUNTRY] [YEAR]
ABOUT THE FEED THE FUTURE SURVEY IMPLEMENTATION TRACKER:
The Feed the Future Survey Implementation Tracker consists of a list of tasks and deliverables designed to help USAID Activity Managers systematically monitor and manage the implementation of surveys conducted for Feed the Future. Although this Tracker was designed to support the implementation of Feed the Future Zone of Influence population-based surveys, it can also be used to guide the implementation of other population-based surveys in developing country contexts (though timelines will need to be adjusted outward if not working with a pre-established set of core survey documents). When each of the steps and deliverables are executed by appropriately trained and experienced staff who are focused on ensuring quality and completeness, it is expected that this approach will produce a survey operation and survey data that are of a minimum defensible quality. This tracker serves as: - a map of the critical aspects of the survey processes that need to be in place to achieve minimum survey methodological standards; - a planning guide to support alignment of survey processes, staff, and resources; - a framework into which other Feed the Future Zone of Influence Survey guidance documents fit, including the survey protocol; questionnaire; and training, interviewer, supervisor, and data management manuals; - a monitoring tool that helps managers to track overall survey progress, technical quality, deliverables, and other management aspects of the survey, and ensure none is skipped or forgotten.
HOW TO USE THE SURVEY TRACKER
Item | Description
Tasks: | All requisite tasks for the survey to be performed by the contractor are pre-filled in the tracker. Managers may adapt the tool by adding other specific tasks that they deem important.
Deliverable: | All key deliverables from each task are pre-filled in the tracker. Managers may wish to add more, depending on the extent to which very close management of the contractor may be required.
Status: | There are four status categories - Not Started, In Progress, Delayed, and Complete. For each task, indicate where it is in the process.
Dates: | All due dates for each deliverable should be discussed and agreed on before they are entered into the Tracker. Timelines vary for each deliverable, and the Survey Manager should use the Gantt Chart as a guide for estimating the dates. One to two weeks should be allowed to review deliverable submissions. Editing and formatting should also allow for two weeks.

## Survey Tracker Mgmt Tool
Key: Status Categories
|  |  |  | Not Started | In Progress | Delayed | Complete
|  |  |  | ON | ON | OFF | ON
Feed the Future Survey Implementation Tracker |  |  |  | Contractor Submission |  | USAID Review |  | Contractor Revision, Editing, and Formatting |  | Submitted | Approved
| Tasks | Deliverables | STATUS | START DATE | END DATE | START DATE2 | END DATE2 | START DATE | END DATE | DATE SUBMITTED | DATE APPROVED | NOTES
1 | Activity planning | Customized scope of work | Delayed | 2017-04-21
2 | Inception visit | Inception visit report | Complete
3 | Develop plan for obtaining ethical review and approval from federalwide-certified and in-country IRBs | Package of all IRB submission requirements for both international and in-country (if required)
4 | Prepare the study design and accompanying implementation plan | Survey protocol | In Progress
5 | Develop a scope of work for local survey implementation partner, issue RFP (if required) | Scope of work (with detailed fieldwork implementation plan, including team structure, fieldwork timeline, and logistics), RFP
6 | Prepare the sampling design | Sampling design plan | Not Started
7 | Coordinate with national statistical office to select primary selection units (PSUs) | List of selected clusters (first stage sampling)
8 | Prepare the analysis plan | Data analysis plan
9 | Undertake country-specific customization of the core questionnaire (paper version) | Customized questionnaire
10 | Translate questionnaire according to established translation protocol (paper version) | Translated questionnaire
11 | Submit application and protocol for review to the IRB | Ethical clearance obtained
12 | Establish range values for purposes of implementing range checks | File of range values (indicating which questionnaire items will have range checks and what the ranges will be)
13 | Prepare unit conversion tables | Excel file indicating local units of measure and conversion factors (to make equivalent to standard units of measure)
14 | Subcontract to local partner organization | Contract signed with local survey organization
15 | Implement questionnaire pretest according to established protocol | Questionnaire pretest report
16 | Arrange for material provisioning (tablet computers, scales, and height boards) | Supply ordering plan and timeline (including customs management plan if supplies are being shipped to country)
17 | Develop pretest and pilot protocols | Pretest and pilot protocols
18 | Program and test the questionnaire (either for tablets or for data entry program) | Questionnaire programming plan
19 | Prepare the survey manuals:
| 19a - Interviewer Manual | Customized Interviewer Manual
| 19b - Supervisor and Field Editor Manual | Customized Supervisor Manual (CAPI) or Supervisor and Field Editor Manual (for PAPI Surveys)
| 19c - Survey Organization Manual | Customized Survey Organization Manual
| 19d - GPS Manual | Customized GPS Manual
| 19e - Quality Control and Support Team Manual | Customized Quality Control and Support Team Manual
| 19f - Listing Manual and List Preparation protocol | Customized Listing Manual and List Preparation protocol
20 | Develop field check tables | Field check table shells
21 | Prepare data structure and codebook | Structure of the data file and expected format of the codebook
22 | Develop and code programming specifications (tablets only) | Programming specification tables
23 | Prepare data cleaning plan | Data cleaning plan
24 | Develop data monitoring plan | Data monitoring plan
25 | Develop fieldwork management and monitoring plan | Detailed fieldwork management and monitoring plan with regular progress reports throughout fieldwork
26 | Develop interviewer training plans and supporting materials:
| 26a - Develop interviewer training plan | Interviewer training plan
| 26b - Develop training agenda (facilitator and trainee versions) | Training agenda (facilitator and trainee versions)
| 26c - Attendance sheets | Customized attendance sheets
| 26d - Quizzes | Quizzes
| 26e - Role play exercises | Role play exercises
| 26f - Demonstration of field check tables and interpretation | Demonstration of field check tables and interpretation
| 26g - Demonstration of real-time remote fieldwork monitoring (if planned) | Demonstration of real-time remote fieldwork monitoring
| 26h - Tablet training materials (if relevant) | Tablet training materials (if relevant)
| 26i - Agriculture-specific training materials | Agriculture-specific training materials
| 26j - Anthropometry training materials | Anthropometry training materials
| 26k - Biomarker training materials (if relevant) | Biomarker training materials (if relevant)
| 26l - Supervisor and field editor training materials (including assignment and control sheets) | Supervisor and field editor training materials (including assignment and control sheets)
| 26m - Data entry staff and supervisor training plan and materials (if relevant) | Data entry staff and supervisor training plan and materials
| 26n - IT staff training plan and materials | IT staff training plan and materials
27 | Implement listing operation | Listing field report and household listing
28 | Implement cleaning of listing data and selection of households (on a rolling basis) | List of households selected for interview
29 | Ensure that IRB approvals have been received | Approval from Federalwide-certified IRB and local IRB
30 | Implement training of trainers (TOT) | Completion of training
31 | Implement pretest (as part of TOT) | TOT and pretest report
32 | Implement main training | Completion of training
33 | Implement pilot (as part of main training) | Main training and pilot report
34 | Implement data entry/data management pilot as part of all-systems fieldwork pilot | Data entry/data management pilot report
35 | Prepare data weighting protocol | Data weighting protocol
36 | Implement fieldwork | Weekly fieldwork report, plus summary fieldwork report at end of data collection activities
37 | Generate fieldcheck tables | Weekly field check tables
38 | Weight the data | Memo advising that the weighting of the data has been completed according to protocol
39 | Prepare protocol for rendering data suitable for public use | Protocol for preparation of public use data
40 | Clean the data | Memo advising of data cleaning steps implemented according to plan, and notable findings during the cleaning process
41 | Prepare data quality assessment memo | Memo to include response rates, final set of field check tables and interpretation of key findings, and any other pertinent information regarding data quality
42 | Analyze the data | Produce frequencies, cross-tabulations, and any additional required statistical analyses
43 | Prepare final report tables | Final report tables (draft, final)
44 | Draft final report text | Final report text (draft, final)
45 | Prepare internal use data files (maintains some PII, e.g., GPS coordinates) | Internal use data file
46 | Prepare public use data files (excludes PII) | Public use data file
47 | Enter values in Feed the Future Monitoring System (FTFMS) | Accessible FTF database
Notes: RFP – request for proposal; PSU – primary sampling unit; IRB – institutional review board; PII – Personally identifiable information; FTFMS – Feed the Future Management System

## Gantt Chart
| Feed the Future Zone of Influence Survey Tasks and Timeline | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Activity planning | bar: MONTH 1
2 | Inception visit | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRBs | bar: MONTH 1
4 | Prepare the study design and accompanying implementation plan | bar: MONTH 1 to MONTH 3
5 | Develop a scope of work for local survey implementation partner, issue RFP (if required) | bar: MONTH 2
6 | Prepare the sampling design | bar: MONTH 2
7 | Coordinate with national statistical office to select primary sampling units | bar: MONTH 2 to MONTH 3
8 | Prepare the analysis plan | bar: MONTH 2 to MONTH 3
9 | Undertake country-specific customization of the core questionnaire (paper version) | bar: MONTH 2 to MONTH 3
10 | Translate questionnaire according to established translation protocol (paper version) | bar: MONTH 3
11 | Submit application and protocol for review to each IRB | bar: MONTH 3 to MONTH 4
12 | Establish range values for purposes of implementing range checks | bar: MONTH 3 to MONTH 4
13 | Prepare unit conversion tables | bar: MONTH 3 to MONTH 4
14 | Subcontract to local partner organization | bar: MONTH 4
15 | Implement questionnaire pretest according to established protocol | bar: MONTH 4 to MONTH 5
16 | Arrange for material provisioning (tablet computers, scales, height boards, GPS units) | bar: MONTH 4 to MONTH 5
17 | Develop pretest and pilot protocols | bar: MONTH 4 to MONTH 5
18 | Program and test the questionnaire (either for tablets or for data entry program) | bar: MONTH 4 to MONTH 6
19 | Prepare the survey manuals: | bar: MONTH 4 to MONTH 6
19a - Interviewer Manual | bar: MONTH 4 to MONTH 6
19b - Supervisor and Field Editor Manual | bar: MONTH 4 to MONTH 6
19c - Survey Organization Manual | bar: MONTH 4 to MONTH 6
19d - GPS Manual | bar: MONTH 4 to MONTH 6
19e - Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
19f - Listing Manual and List Preparation Protocol | bar: MONTH 4 to MONTH 6
20 | Develop field check tables | bar: MONTH 4 to MONTH 7
21 | Prepare data structure and codebook | bar: MONTH 4 to MONTH 7
22 | Develop and code programming specifications (tablets only) | bar: MONTH 4 to MONTH 7
23 | Prepare data cleaning plan | bar: MONTH 4 to MONTH 7
24 | Develop data monitoring plan | bar: MONTH 4 to MONTH 7
25 | Develop fieldwork management and monitoring plan | bar: MONTH 4 to MONTH 7
26 | Develop interviewer training plans and supporting materials | bar: MONTH 4 to MONTH 7
26a - Training plan | bar: MONTH 4 to MONTH 7
26b - Agenda (facilitator and trainee versions) | bar: MONTH 4 to MONTH 7
26c - Attendance sheets | bar: MONTH 4 to MONTH 7
26d - Quizzes | bar: MONTH 4 to MONTH 7
| Feed the Future Zone of Influence Survey Tasks and Timeline (cont.) | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
26e - Role play exercises | bar: MONTH 4 to MONTH 7
26f - Demonstration of field check tables and interpretation | bar: MONTH 4 to MONTH 7
26g - Demonstration of real-time remote fieldwork monitoring (if planned) | bar: MONTH 4 to MONTH 7
26h - Tablet training materials (if relevant) | bar: MONTH 4 to MONTH 7
26i - Agriculture-specific training materials | bar: MONTH 4 to MONTH 7
26j - Anthropometry training materials (if relevant) | bar: MONTH 4 to MONTH 7
26k - Biomarker training materials (if relevant) | bar: MONTH 4 to MONTH 7
26l - Supervisor and field editor training materials (incl. assignment and control sheets) | bar: MONTH 4 to MONTH 7
26m - Data entry staff and supervisor training plan and materials (if relevant) | bar: MONTH 4 to MONTH 7
26n - IT staff training plan and materials | bar: MONTH 4 to MONTH 7
27 | Implement listing operation | bar: MONTH 6 to MONTH 7
28 | Implement cleaning of listing data and selection of households (on a rolling basis) | bar: MONTH 6 to MONTH 7
29 | Ensure that IRB approvals have been received | bar: MONTH 7
30 | Implement training of trainers | bar: MONTH 7 to MONTH 8
31 | Implement pretest (as part of training of trainers) | bar: MONTH 7 to MONTH 8
32 | Implement main training | bar: MONTH 8
33 | Implement pilot (as part of main training) | bar: MONTH 8
34 | Implement data entry/data management pilot as part of all-systems fieldwork pilot | bar: MONTH 8
35 | Prepare data weighting protocol | bar: MONTH 8
36 | Implement fieldwork | bar: MONTH 9 to MONTH 13
37 | Generate field check tables | bar: MONTH 9 to MONTH 14
38 | Weight the data | bar: MONTH 14
39 | Prepare protocol for rendering data suitable for public use | bar: MONTH 14
40 | Clean the data | bar: MONTH 14 to MONTH 15
41 | Prepare data quality assessment memo | bar: MONTH 16
42 | Analyze the data | bar: MONTH 16 to MONTH 19
43 | Prepare the final report tables | bar: MONTH 18 to MONTH 19
44 | Draft the final report text | bar: MONTH 17 to MONTH 19
45 | Prepare internal use data files (maintains some PII, e.g., GPS coordinates) | bar: MONTH 17 to MONTH 20
46 | Prepare public use data files (excludes PII) | bar: MONTH 18 to MONTH 20
47 | Enter values in Feed the Future Monitoring System (FTFMS) | bar: MONTH 20
Notes: RFP – request for proposal; PSU – primary sampling unit; IRB – institutional review board; PII – personally identifiable information
This Gantt chart is predicated on the availability of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized according to country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented in this chart.

## ref
StatusCats
Not Started | Not Started
In Progress | In Progress
Delayed | Delayed
Complete | Complete