## Tr. Timeline
FEED THE FUTURE SURVEY TRAINING TIMELINE: TRAINING OF TRAINERS THROUGH THE START OF MAIN FIELDWORK
ACTIVITY | DAYS
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
ToT—Survey content
ICDM training
ToT—Tablet training
Tablet pretest and debriefing
Updates to CAPI program
Main training—Survey content
Field practice and debriefing
Main training—Tablet training
Supervisor & QCS training
Pilot and debriefing
Fieldwork logistics
Final updates to CAPI program*
* Updates to CAPI program will also take place thoughout training.

## Pretest Tr.
QUESTIONNAIRE PRETEST TRAINING
Venue: [ENTER LOCATION]
Duration: 5 days
Trainees: 21 trainees (5 teams with 2 interviewers, 1 agriculture interviewer and 1 supervisor per team) and 1 data manager
Day/Date | Morning | Afternoon
Day 1 | General | Questionnaire Content
[DATE, 2018] | Importance of surveys and research for policymaking Global Food Security Strategy survey objectives Research ethics and human subject protection | Cover page, informed consent Module 1 - Household roster Module 2 - Dwelling characteristics
Purpose of the Questionnaire Pretest
PowerPoint presentation (.ppt pretest training) Understanding of the intent of each question Understanding non-verbal cues
Day 2 | Questionnaire Content | Questionnaire Content
[DATE, 2018] | Module 3 - Food security & resilience Module 4 - Women's nutrition | Module 5 - Children's nutrition Module 6 - A-WEAI
Day 3 | Questionnaire Content | Questionnaire Content
[DATE, 2018] | Module 7 - Agriculture technologies | Module 8 - Household consumption expenditure
Day 4 | Mock interviews and role-plays | Cognitive Probes
[DATE, 2018] | Practice interviewing, observing, and note-taking techniques | Importance of pretesting the questionnaire using cognitive probes
Intent of each cognitive probe
Day 5 | Pretest form | Mock interviews and role-plays
[DATE, 2018] | Questionnaire pretest observation checklist Recording observations on the pretest qualitative data entry form | Practice interviewing, observing, and note-taking techniques
Pretest report
Contents of the pretest report

## Interviewer's Tr.
INTERVIEWER'S TRAINING
Venue: [ENTER LOCATION]
Duration: 18 days
Trainees: 70 interviewers, 20 supervisors, 1 data manager, 1data manager's assistant, and 1 IT specialist
Day/Date | Morning | Afternoon
Day 1 | Welcome and introductions | Overview of the survey documents
[DATE, 2018] | Importance of surveys and research for policymaking | Survey Training Manual
| Global Food Security Strategy survey objectives | Organization Manual and other field manuals
| Organization of survey—planning, training, data collection, data processing, analysis, and reporting | Anthropometry, land area, and GPS coordinate measurements and field forms
| Research ethics and human subjects protection | Overview of the questionnaire, module-by-module
Day 2 | Questions from Day 1 | Questionnaire discussion:
[DATE, 2018] | Organization of fieldwork | Module 1: Household Roster
| General interviewing techniques | QxQ instructions for module 1
| Sample and eligibility criteria—primary decisionmakers | Practice entering responses on the paper questionnaire
Household identification and informed consent
Interviewer's manual and QxQ instructions
Day 3 | Review of Day 2 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 2: Dwelling Characteristics
| Module 2: Dwelling Characteristics | QxQ instructions for module 2
| QxQ instructions for module 2 | Practice entering responses on the paper questionnaire
Day 4 | Review of Day 3 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 3: Food Security and Resilience
| Module 3: Food Security and Resilience | QxQ instructions for module 3
| QxQ instructions for module 3 | Practice entering responses on the paper questionnaire
Day 5 | Review of Day 4 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 4A: Women's Anthropometry (social interviewers)
| Module 4: Women's Nutrition (social interviewers) | QxQ instructions for module 4A
| QxQ instructions for module 4 | Module 7: Agriculture Technologies (ag interviewers)
| Module 7: Agriculture Technologies (ag interviewers) | QxQ instructions for module 7
| QxQ instructions for module 7 | Practice entering responses on the paper questionnaire (all interviewers)
Day 6 | Review of Day 4 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 5A: Children's Anthropometry (social interviewers)
| Module 5: Children's Nutrition (social interviewers) | QxQ instructions for module 5A
| QxQ instructions for module 5 | Module 7: Agriculture Technologies (ag interviewers)
| Module 7: Agriculture Technologies (ag interviewers) | QxQ instructions for module 7
| QxQ instructions for module 7 | Practice entering responses on the paper questionnaire (all interviewers)
INTERVIEWER'S TRAINING (CONTINUED)
Day 7 | Review of Day 6 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 6: A-WEAI
| Module 6: A-WEAI | Practice entering responses on the paper questionnaire
| QxQ instructions for module 6 | Mock interviews
Day 8 | Review of Day 7 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 8: Household Consumption Expenditure
QxQ instructions for module 8
| Module 8: Household Consumption Expenditure | Practice entering responses on the paper questionnaire
| QxQ instructions for module 8 | Mock interviews
Day 9 | Review of Day 8 | Questions and answers
[DATE, 2018] | Women's and Children's Anthropometry—demonstration and practice | Women's and Children's Anthropometry—practice
| Practice recording measurements on anthropometry forms | Practice recording measurements on anthropometry forms
| Measurement of land area and crop productivity Recording measurements on the tablet | Measurement of land area and crop productivity Recording measurements on the tablet
Day 10 | Field Day
[DATE, 2018] | Women's and Children's Anthropometry practice in a school or health center | Women's and Children's Anthropometry practice in a school or health center
| Measurement of land area and crop productivity on agricultural land | Measurement of land area and crop productivity on agricultural land
Day 11 | Field Day
[DATE, 2018] | Women's and Children's Anthropometry practice in a school or health center | Women's and Children's Anthropometry practice in a school or health center
| Measurement of land area and crop productivity on agricultural land | Measurement of land area and crop productivity on agricultural land
Day 12 | Group discussions
[DATE, 2018] | Field observations and discussions | Mid-training Quiz—Survey and Questionnaire
Questions and clarifications
Day 13 | Introduction to CAPI (.ppt) | CAPI menus (.ppt)
[DATE, 2018] | Distribute tablets | Provide training cluster numbers and team numbers
| Tablet basics (.ppt) | Assigning households (.ppt)
| Keying exercise | Assign two households per interviewing team, one at a time
Assign households with farmers to the ag interviewer
Question and answers
Day 14 | CAPI household schedule (.ppt), one screen at a time | Household module status (.ppt)
[DATE, 2018] | Demonstration | Facilitators check and collect
| Trainers lead interviewers in entering practice household data | Fill out anthropometry form
| Data entry demo points (.ppt)—all points check listed | Data transfer (.ppt)
| Trainers lead interviewers in entering practice household data | Transfer all data to supervisor, facilitators check by listing cluster on supervisor tablet
INTERVIEWER'S TRAINING (CONTINUED)
Day 15 | Upgrades (.ppt) | Second interviewer assignment
[DATE, 2018] | Verify that all trainees receive upgrades (date appears on the menu if successful) | Interviewers to pair up male and female and complete male and female WEAI modules
| CAPI modules | Interviewers work to complete remaining modules
| Review household module status Re-accessing module questionnaires Interviewers complete modules 4 and 5 | Submit all data to supervisors
Day 16 | Mock interviews and role-playing | Practice, practice, practice!
[DATE, 2018] | Trainees interview each other using pre-filled paper questionnaire | Trainees interview each other using pre-filled paper questionnaire
Submit all data to supervisors
Day 17 | Entering anthropometry and agricultural data | Classroom simulation
[DATE, 2018] | Enter anthropometry forms filled during Day 4 (social interviewers) Collect and enter agricultural data (ag interviewers) Scanning transmittal sheets | Mock interviews in languages, set up a simulation Facilitators MUST observe and provide feedback on interviewing skills
| Language practice | CAPI extras
| Mock interviews in languages, testing of translations Facilitators MUST observe and provide feedback on interviewing skills | Cover error messages and any additional outstanding CAPI issues
Day 18 | CAPI test | Closing clusters
[DATE, 2018] | Closing clusters, submitting data to central office | Facilitators observe teams close clusters and congratulate each team
| PowerPoint presentation (closing clusters.ppt) | Any other topics, questions, or issues Download practice fieldwork upgrade
| Facilitators observe teams close clusters and congratulate each team | Close clusters, submit data to supervisor and to central office
End of Training Quiz—CAPI entry and errors
Note: Each morning and evening, teams should transfer data to the supervisor, and the supervisor should download any upgrades.
Practice households should have a primary male decisionmaker, a primary female decisionmaker, and at least one child under age 6.

## Tr. of Trainers
TRAINING OF TRAINERS
Venue: [ENTER LOCATION]
Duration: 13 days
Trainees: 15 to 20 experienced survey staff and 1 data manager
Day/Date | Morning | Afternoon
Day 1 | Welcome and introductions | Overview of the survey documents
[DATE, 2018] | Importance of surveys and research for policymaking | Survey Training Manual
| Global Food Security Strategy survey objectives | Organization Manual and other field manuals
| Organization of survey—planning, training, data collection, data processing, analysis, and reporting | Anthropometry, land area, and GPS coordinate measurements and field forms
| Research ethics and human subjects protection | Overview of the questionnaire, module-by-module
Day 2 | Questions from Day 1 | Questionnaire discussion:
[DATE, 2018] | Organization of fieldwork | Module 1: Household Roster
| Sample and eligibility criteria—primary decisionmakers | Module 2: Dwelling Characteristics
| Completing the cover page and informed consent | QxQ instructions for modules 1 and 2
| Interviewer's manual and QxQ instructions | Practice entering on the paper questionnaire
Day 3 | Review of Day 2 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 4: Women's Nutrition
| Module 3: Food Security and Resilience | QxQ instructions for module 4
| QxQ instructions for module 3 | Practice entering on the paper questionnaire
Day 4 | Review of Day 3 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Women's and Children's Anthropometry—demonstration and practice
| Module 5: Children's Nutrition | Practice recording measurements on anthropometry forms
QxQ instructions for module 5
Day 5 | Review of Day 4 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Module 6: A-WEAI
| Module 6: A-WEAI | Practice entering on the paper questionnaire
QxQ instructions for module 6
Day 6 | Review of Day 5 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | Practice entering on the paper questionnaire
| Module 7: Agriculture Technologies | Measurement of land area and crop yield
| QxQ instructions for module 7 | Assignment of households with farmers to agricultural interviewers
Day 7 | Review of Day 6 | Questionnaire discussion:
[DATE, 2018] | Questionnaire discussion: | QxQ instructions for module 8
| Module 8: Household Consumption Expenditure | Practice entering on the paper questionnaire
QxQ instructions for module 8
TRAINING OF TRAINERS (CONTINUED)
Day 8 | Review of Day 7 | 3. CAPI menus (.ppt)
[DATE, 2018] | 1. Introduction to CAPI (.ppt) | Provide training cluster numbers and team numbers
| Distribute tablets | 4. Assigning households (.ppt)
| 2. Tablet basics (.ppt) | Assign two households per person, one at a time
| Keying exercise | Question and answers
Day 9 | 5. CAPI household schedule (.ppt), one screen at a time | 7. Household module status (.ppt)
[DATE, 2018] | Demonstration | Facilitators check and collect
| Trainers lead interviewers in entering practice household data | Fill out anthropometry form
| 6. Data entry demo points (.ppt)—all points check listed | 8. Data transfer (.ppt)
| Trainers lead interviewers in entering practice household data | Transfer all data to supervisor, facilitators check by listing cluster on supervisor tablet
Day 10 | 9. Upgrades (.ppt) | 11. Second interviewer assignment
[DATE, 2018] | Verify that all trainees receive upgrades (date appears on the menu if successful) | Interviewers pair up male and female and complete male and female WEAI modules
| 10. CAPI modules | Interviewers work to complete remaining modules
| Review household module status Re-accessing module questionnaires Interviewers complete modules 4 and 5 | Submit all data to supervisors
Day 11 | 12. Mock interviews and role-playing | 13. Practice, practice, practice!
[DATE, 2018] | Trainees interview each other using pre-filled paper questionnaire | Trainees interview each other using pre-filled paper questionnaire
Submit all data to supervisors
Day 12 | 14. Entering anthropometry | Classroom simulation
[DATE, 2018] | Enter anthropometry forms filled during Day 4 Scanning transmittal sheets | Mock interviews in languages, set up a simulation Facilitators MUST observe and provide feedback on interviewing skills
| Language practice | 15. CAPI extras
| Mock interviews in languages, testing of translations Facilitators MUST observe and provide feedback on interviewing skills | Cover error messages and any additional outstanding CAPI issues
Day 13 | CAPI test | Closing clusters
[DATE, 2018] | 16. Closing clusters, submitting data to central office | Facilitators observe teams close clusters and congratulate each team
| PowerPoint presentation (closing clusters.ppt) | Any other topics, questions, or issues Download practice fieldwork upgrade
| Facilitators observe teams close clusters, and congratulate each team | Close clusters, submit data to supervisor and to central office
Note: Each morning and evening, teams should transfer data to the supervisor, and the supervisor should download any upgrades.
Practice households should have a primary male decisionmaker, a primary female decisionmaker, and at least one child under age 6.

## Supervisor's Tr.
SUPERVISOR'S TRAINING
Venue: [ENTER LOCATION]
Duration: 1 day
Trainees: 20 supervisors and 6-8 quality control supervisors
Day/Date | Morning | Afternoon
Day 1 | Roles and responsibilities of the supervisors | Review of field forms
[DATE, 2018] | PowerPoint presentation (.ppt Supervisor's training) Field Supervisor's Manual Supplies and logistics Communication and payments Organize and supervise: 1. Contact local authorities 2. Locate selected clusters and households 3. Opening, closing, finalizing clusters 4. Assign households to interviewers 5. Conduct spot-checks 6. Conduct team meetings | Household forms Interviewer's assignment sheet Roster spot-checks Review height and weight data Review GPS coordinates and measures of plot area Household form archiving, backup, and transmission
| Field observations | Reporting forms
| 1. Interview observations 2. Check for presence of male and female primary decisionmakers, age heaping, age displacement in women and children, expected number of eligible women and children, for respective modules 3. Status of clusters, response rates, vacant homes, etc. 4. Correct household, GPS coordinates, land area measurement, etc. | Supervisor's assignment sheet Transmission of data to the central office Archive data to Dropbox
Note: In addition to the one-day training, supervisors must participate in the interviewer's training.

## QCS Tr.
QUALITY CONTROL AND SUPPORT (QCS) TEAM TRAINING
Venue: [ENTER LOCATION]
Duration: 1 day
Trainees: 6-8 QCS supervisors
Day/Date | Morning | Afternoon
Day 1 | Roles and responsibilities of the QCS Team members | Review of field forms
[DATE, 2018] | PowerPoint presentation (.ppt QCS training) Quality Control and Support Manual | Interviewer's and supervisor's assignment sheet Roster spot-checks
| Review of field documents and observations | Reporting forms
| 1. Interview observations 2. Meeting with local authorities 3. Presence of male and female primary decisionmakers, age heaping, age displacement in women and children, expected number of eligible women and children, for respective modules 4. Status of clusters, response rates, vacant homes, etc. 5. Correct household, GPS coordinates, land area measurement, etc. 6. Household form archiving, backup, and transmission 7. Field supervisor conducting a team meeting, etc. | 1. Data quality control report follow-up 2. Interview observation 3. Feedback on field supervisor observation of an interview 4. General field team QC report form 5. Team debriefing report 6. Field team resupply checklist 7. Provision of human resources support to field teams
Note: In addition to the one-day training, Quality Control & Support Team members must participate in the interviewer's and supervisor's training

## ICDM Tr.
IN-COUNTRY DATA MANAGER'S TRAINING
Venue: [ENTER LOCATION]
Duration: 2 days
Trainees: 1 In-country data manager (ICDM), 1 ICDM research assistant, and 1 IT specialist
Day/Date | Morning | Afternoon
Day 1 | CENTRAL OFFICE PROCESSING
[DATE, 2018] | Introduction to main responsibilities | ICDM menu
| PowerPoint presentation (.ppt slides a-b) Purpose of ICDM and relationship with [CONTRACTOR] and field/survey teams Importance of data quality, organization, following guidelines Overall flow of data processing and general responsibilities to teams, survey management | ICDM Manual Purpose of menu, loading ICDM menu, identifying cluster Review each step of menu and importance of carrying them out in order Review programs that are run in each step and where data are located
| Set up of ICDM computer and server | Structure check and secondary editing
| PowerPoint presentation (.ppt slides a-b) Requirement for consistent internet Work with implementing [SUBCONTRACTOR] to establish internet and server connections in line with [SUBCONTRACTOR] policy Install Dropbox, CSPro, MS Office | ICDM Manual Run structure check and secondary editing on practice fieldwork clusters Importance of not fabricating data Guidance for addressing each error that may appear Practice editing and modifying data where necessary
| Downloading and saving data | Finalizing clusters
| PowerPoint presentation (.ppt slides a-b) Connect computer and server to Dropbox and download data from practice fieldwork Confirm that connection is in place and data are downloaded to proper location Determine when clusters are available for download | PowerPoint presentation (.ppt slides a-b) Purpose of finalizing clusters Point when clusters can be finalized Organization of work
Day 2 | FIELD MONITORING
[DATE, 2018] | Field check tables | Tablet maintenance
| PowerPoint Presentation (.ppt slides a-b, ICDM manual) Purpose of field check tables Responsibility of ICDM in reviewing tables Reporting of issues Comparison of tables by team, interviewer Content of each table | PowerPoint presentation (.ppt slides a-b) Standard problems with tablets Repairing tablets if possible Communication with teams and remote access to tablets
| Recording issues | Communication protocols
| ICDM manual Communication of issues Recording of unresolved issues and questions | ICDM manual Review of ICDM responsibility Who to contact for which issues Leadership of data processing and data quality
| Fieldwork progress | Any other issues
| PowerPoint presentation (.ppt slides a-b) Definition of columns in progress report Identifying bottlenecks in data processing Frequency of checks | Any other issues Question and answers